## Sheet1
Task ID | Task Name | Description | Owner | Deadline | Status
1 | Project Initialization & Setup | Create React app, configure ESLint, Prettier, Git repo, install dependencies | Senior Developer / Team Lead | TBD | Pending
2 | Core Layout Development | Header, Sidebar, Footer, React Router setup | UI Developer | TBD | Pending
3 | Reusable Components | Buttons, Inputs, Modals, Toast notifications, Tables | Mid-Level Developer | TBD | Pending
4 | Authentication Module UI | Login form, Forgot password, Logout | Junior Developer | TBD | Pending
5 | Dashboard Page | Summary cards, Chart.js integration, Recent activities | Mid-Level Developer | TBD | Pending
6 | Room Management Module | Room listing, Add/Edit/Delete rooms, Search & filter | Junior Developer | TBD | Pending
7 | Reservation Management Module | List reservations, Add/Edit forms with date pickers, Cancel reservation | Mid-Level Developer | TBD | Pending
8 | Customer Management Module | Customer list, Profile view/edit | Junior Developer | TBD | Pending
9 | Billing & Invoice Pages | Generate invoice UI, Billing summary | Mid-Level Developer | TBD | Pending
10 | Reports Module | Generate reports with filters, Chart.js reports | Senior Developer | TBD | Pending
11 | Settings & Profile Pages | User profile edit, Application settings UI | Junior Developer | TBD | Pending
12 | Responsive & Cross-Browser Testing | Test and fix responsiveness and browser compatibility | QA / UI Developer | Ongoing | Pending
13 | Code Review & Documentation | Review PRs, maintain documentation, enforce code standards | Team Lead & Senior Developers | Ongoing | Pending